## Sheet1
Example Safety Leadership Challenge project plan
Start date: DD/MM/YY | time axis 2017-01-01 to 2017-03-04
Description of task | time axis 2017-01-01 to 2017-03-04
Identify current safety issues and focus of challenge
Consult with internal stakeholders to understand extent and scope of issues
Develop business case for presentation to senior management
Milestone 1 | Business case developed and presented
Form steering committee and project team
Conduct vision-setting workshop
Conduct action and project planning workshop
Allocate roles and responsibilities, identify resourcing requirements
Present to steering committee/senior management and seek approval
Milestone 2 | Project planning completed
Identify communications stakeholders
Develop communications strategy
Develop communications materials
Milestone 3 | Implement communications strategy
Identify evaluation strategy
Collect baseline evaluation data
Develop implementation strategy
Conduct briefings to project and supply chain staff
Milestone 4 | Baseline data collected
Implement and monitor challenge actions
Milestone 5 | Safety Leadership Challenge actions implemented
Collect follow-up evaluation data
Milestone 6 | Evaluation of challenge completed
Communicate challenge results to project staff (and external stakeholders, if applicable)
Close-out project
| LEGEND: | 2017-01-02: indicates estimated task time
indicates estimated milestone delivery date